## BERAP2023
STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) 2023
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date
1 | Improved transparency in Land Administration and Land-based Investment Process | (i) This reform area will enhance the administration and management of land in Taraba State; (ii) the reform will also improve trasparency of property registration and unlock capital from this asset class. | A.1. Develop and adopt a long term vision, goals and strategic directions for land and property administration in Taraba State | Develop a high level strategy document defining a shared vision, measurable goals and strategic direction for land and property administration in Taraba State | Taraba State Geo Information Service GIS | Office of the Governor, Office of the Secretary to the State Government, Ministry of Finance, Budget, and Economic Planning, Ministry of Justice , Bureau of Lands and Survey, Ministry of Rural & Urban Development, Taraba State Internal Revenue Service, Taraba State Investment Promotion Agency, Ministry of Agriculture and Food Security | N10,004,000.00 | 2023-01-01 | 2023-10-31
|  |  | A.2. Establish and build consesus among relevant MDAs on institutional and policy reforms being proposed and/or implemented including but not limited to developing and maintaining digital titling of all landed properties in Taraba | Ensure at least 50% of buildings in major towns) are enunerated and recorded | Taraba State Geo Information Service GIS | Office of the Governor, Office of the Secretary to the State Government,Ministry of Finance, Budget, and Economic Planning, Ministry of Justice , Bureau of Lands and Survey, Ministry of Housing & Urban Development, Taraba State Internal Revenue Service, Taraba State Investment Promotion Agency, Ministry of Agriculture and Food Security |  | 2023-01-01 | 2023-10-31
|  |  | B.1. Publish the process for obtaining CofO including all relevant MDAs, time frames and costs on the State official website | The Bureau of Land and Survey in collaboration with Taraba State Geospatial Centre shall provide comprehensive information on the process of obtaining Certificate of Occupancy in Taraba State. The user, beneficiairies and recipients of the reform include applicants for land CofO, investors and business owners | Taraba State Geo Information Service GIS | Taraba State Internal Revenue Services,Ministry of Finance, Budget, and Economic Planning | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | B.2. Publish the process for obtaining construction permit including all relevant MDAs, time frames and costs on the State official website | The Ministry of Rural & Urban Development shall provide comprehensive information on the process of obtaining Constrution permits in Taraba State. The user, beneficiairies and recipients of the reform include applicants for construction permit, investors and business owners | Ministry of Rural & Urban Development | Taraba State Internal Revenue Services,Ministry of Finance, Budget, and Economic Planning | Not Applicable | 2023-01-01 | 2023-12-31
|  |  | B.3. Develop the Terms of Reference (ToR) for creation of data-centric digital archive of CofOs with a serchable indexes with a searchable index in accrodance with international standards | The Bureau of Lands and Surve in collaboration with the Taraba State Geographical Informatoon System project will ensure end-to-end processing of land transactions at the data center and digital archiving of the electronically signed registered CofOs and other instruments | Taraba State Geo Information Service GIS | Ministry of Rural & Urban Development, Office of the Surveyor General and Ministry of Finance, Budget, and Economic Planning | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | B.4. Digitization and indexation of existing CofOs in a digital archive | Ensure at least 75% of existing certificates are digitzed and archived. | Taraba State Geo Information Service GIS | Ministry of Finance, Budget, and Economic Planning | N125,000,000.00 | 2023-01-01 | 2023-06-30
|  |  | C. Establishment the Framework for Responsible and Inclusive Land Intensive Agriculture (FRILIA) | (i) Set-up FRILIA Steering Committee to develop FRILIA document to address challenges in Land administration for Agricultural and Industrial purposes in the State; (ii) create a Multistakeholders platfrom (MSP) for consultation on key issues | Ministry of Agriculture and Food security | Bureau of Lands and Survey, Office of Surveyor-General, Ministry of Finance, Agriculture Development Project, Farm Settlement, Ministry of Industry, Trade & Investment,Taraba State Investment Promotion Agency, Taraba State Internal Revenue Service, Ministry of Justice | N40,000,000.00 | 2023-01-25 | 2023-10-31
|  |  | C.1. Issuaance of Executive Order on FRILIA | The Steering Committee shall develop an Executive Order on FRILIA for review by the Ministry of Justice, before execution by the Governor. | Ministry of Agriculture and Food security | Bureau of Land and Survey, Ministry of Justice, | N5,000,000.00 | 2023-07-03 | 2023-10-31
|  |  | C.2. Adoption and implementation of the FRILIA | FRILIA Steering Committee shall ensure the adoption and implementation of FRILIA in the State | Ministry of Agriculture and Food security | Bureau of Lands and Survey, Office of Surveyor-General, Ministry of Finance, Farm Settlement, Ministry of Industry, Trade & Investment, Taraba State Investment Promotion Agency, Committee on Agriculture in the State House of Assembly | N5,000,000.00 | 2023-08-01 | 2023-10-31
2 | Improved infrastructure for enhacement of business-enabling environment (regulatory framework for private investment in fibre optic infrastructure) | To build a strong foundation for digital economy through enhaced fast, relaible and accessible fixed broadband to incentivised opertaors for the deployment of fixed broadband in the State. | A. Amendment of the existing legislation/regulations or passing of new legislation/regulation to adopt aggregate fees charged for broadband deployment on a per liner meter basis at a maximum of NGN145 per meter | issue Executive Order or pass legislation passed by the State House of Assembly | Ministry of Rural & Urban Development | Taraba State Internal Revenue Service, Ministry of Finance, Taraba State Investment Promotion Agency, Ministry of Works & Infrastructure Development, and Ministry of Justice | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | A.1. maintenace of the aggregate per linear meter fees for broadband deployment | Ensure a law that caps the Right of Way tariff at not more than N145 per linear meter is enacted. | Ministry of Works & Infrastructure Development | Ministry of Works & Infrastructure Developments, Ministry of Rural & Urban Development | Not Applicable | 2023-03-31 | 2023-10-31
|  |  | B. publication of Right of Way (ROW) process | Publish the ROW process on the State website | Ministry of Rural & Urban Development | Bureau of Information and Communication Technology, Ministry of Rural & Urban Development, Ministry of Infrastructure and Public Utility | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | B.1 Establishment of framework for the ROW process in the State | Establish a framework for ROW deployment across the State | Ministry of Rural & Urban Development | Ministry of Works & Infrastructure Developments | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | B.2. Publish on the state official website, the process for obtaining ROW including all relevant MDAs, timeframes, and costs | Publish all ROW related processes and fees on the State website. | Ministry of Rural & Urban Development | Bureau of Information and Communication Technology, Taraba State Investment Promotion Agency, Ministry of Works & Infrastructure Developments | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | C. deployment of non- Gigabit Passive Optical Network (GPON) fibre optic cable kilometres | Ensure deployment of GPON fibre infrastructure across Taraba State in at least 2,000km across the State. | Ministry of Works & Infrastructure Developments | Ministry of Rural & Urban Development, Office of the surveyor General and Ministry of Finance, Bureau of Information, Communication and Technology | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | C.1 increase in total deployed GPON fibre optic cable kilometres against 2022 baseline meets target. Basic target: 20-99% Stretch target: ˃100% | The State shall ensure that ther is an increase of more that 100% in the total deployed GPON fibre optic cable kilometers against 2022 as baseline | Ministry of Rural & Urban Development | Taraba State Development and Investment Promotion Agemcy, Ministry of Housing and Bureua of Lands | Not Applicable | 2023-01-01 | 2023-10-31
3 | Sustainable Large- Scale Investments | (i) to have an effective State invetsment promotion agency for service delivery to investors and targeted efforts towards attracting and retaining investment (ii) to ensure transparency and easier access to information and participation for stimulation of investment in the economy of the State; (iii) to establish effective Public-Private Partnership (PPP) models in the State | A. mandate Taraba Development and Investment Promotion Agency (TIPA) (state-level technical unit/agency) as the lead organization to facilitate PPP and promote investment into the State | Enact a Law establishing a State Investment Promotion Agency and develop a strategic plan to operationalise the agency. | Taraba State Investment Promotion Agency (TIPA) | Ministry of Industry, Trade and Investment, and the Ministry of Justice | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | A.1. obtain the approval of the State Executive Council (EXCO) mandating TIPA as the lead agency to facilitate PPP and promote investment into Taraba State | Enact and implement a State Public Private Partnership Law designatingTIPA as lead agency for PPP facilitation | Taraba State Investment Promotion Agency | Ministry of Industry, Trade and Investment, Ministry of Justice and Taraba State House of Assembly | Not Applicable | 2023-01-01 | 2023-10-31
|  |  |  | Enact and implement a State Public Private Partnership Law designatingTIPA as lead agency for PPP facilitation | Taraba State Investment Promotion Agency | Ministry of Industry, Trade and Investment, Ministry of Justice and Taraba State House of Assembly | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | B. Establishment of effective PPP models | Develop and agree frameworks to determine the PPP models required for various investment opportunities in the State. | Taraba State Investment Promotion Agency | Ministry of Industry, Trade and Investment, and the Ministry of Justice | N50,000,000.00 | 2023-01-01 | 2023-12-31
|  |  | B.1 establishment of Taraba State Fiscal Commitment and Contigent Liability (FCCL) Management Framework | Develop and obtain State EXCO approval for a Fiscal Commitment and Contigency Liability Management Framework | Ministry of Finance, Budget, and Economic Planning | Ministry of Budget and Economic Planning, TIPA | N2,500,000.00 | 2023-01-01 | 2023-10-31
|  |  | B.2 establishment of PPP legal and institutional framework, inluding guidelines and manual | TIPA to develop guidelines and manual of PPP framework. The beneficiaries are the investors and business owners. | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | N1,000,000,00 | 2023-01-01 | 2023-10-31
|  |  | B.3 establishment of the PPP disclosure Framework | PPP franework established and published on TIPA website | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | N1,000,000,00 | 2023-01-01 | 2023-10-30
|  |  | B.4 online publication of the (i) PPP Fiscal Commitment and Contigent Liability (FCCL) Management Framework; and (ii) PPP legal and institutional framework, including guidelines and manual; and (iii) PPP disclosure framework | (i) Amendment of Taraba PPP Law to include FCCL Management framework (ii) PPP Guidelines and manual to be developed (III) PPP disclosure frameworkto be implemented | Taraba State Investment Promotion Agency | Ministry of Justice | Not Applicable | 2023-01-01 | 2023-10-30
|  |  | B.5. adoption and disclosure of PPP pipeline by TIPA (of which at least 50% is linked to climate adaptation and mitigation | Publish a list of PPP projects and their respective status to promote transparency. | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | Not Applicable | 2023-01-01 | 2023-10-30
|  |  | B.6. online publication (or web-based disclosure portal) of the pipeline projects | TIPA to publish pipeline projects on her website. The beneficiaries are the potential investors, investors and business | Taraba State Investment Promotion Agency | Ministry of Information and Re-Orientation | Not Applicable | 2023-01-01 | 2023-10-30
|  |  | C. establishment of State Project Facilitation Fund with a minimum funding of 3% of the total pipeline estimated capital investment | Establisha State Wealth Fund which will include Project Facilitation Fund to catalyze private investments | Ministry of Finance, Budget, and Economic Planning | Taraba State Investment Promotion Agency, Ministry of Budget ,and Economic Planning, Ministry of Justice, and Ministry of Commerce, Trade & Industry | N500,000,000 | 2023-01-01 | 2023-10-30
|  |  | D. develop/update an inventory/database of all investment incentives (Federal and State) available in Taraba State | Inventory of all investment incentives in the State alreadydeveloped and published on TIPA website. The beneficiaries are the investors and bussiness owners. | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | Not Applicable | 2023-01-01 | 2023-10-30
|  |  | D.1. online publication of the inventory all investment incentives available in the State | Inventory of all investment incentives in the State already published on TIPA website. The beneficiaries are the investors and bussiness owners. | Taraba State Investment Promotion Agency | Bureau of Information and Communication Technology | Not Applicable | 2023-01-01 | 2023-12-31
|  |  | E. Update of TIPA website with required information (including information on access to credit) | TIPA website to be updated with required information. The beneficiaries are the investors, business owners and potential investors | Taraba State Investment Promotion Agency | Bureau of Information and Communication Technology | N10,000,000.00 | 2023-01-01 | 2023-10-30
|  |  | F. organization of quaterly information sessions annually for investors by TIPA | Ensure at least 2 sessions are held in 2023 to engage with investors operating in Taraba State, to discuss among others Business Environment Reforms and tax compliance. | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry And Taraba State Internal Revenue Service | N5,000,000.00 | 2023-01-01 | 2023-10-31
|  |  | G. development and adoption of aftercare and retention program | Develop and implement an aftercare programe that caters to existing investors. | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | N1,500,000.00 | 2023-01-01 | 2023-10-31
4 | Increased Transparency of official fees and procedures | (i) This reform area will increase transparency of official fees and procedures focusing on key business environment enabling MDAs in Taraba State; (ii) the reform will give easier access to regular information for greater regulatory efficiency, lower compliance costs and better regulatory quality; (iii) Reduce overlapping of licensing requirements; (iv) reduce potential discretionary behaviors | A. mapping and developing business regulatory processes in 5 BEE MDAs | Taraba State Ministry of Finance shall work with the selected BEE MDAs to develop a business regulatory processes inclusive of fee structures in the State. | Ministry of Finance, Budget, and Economic Planning | Taraba State Investment Promotion Agency, Ministry of Housing, Taraba State Signage and Advertising Agency, and Bureua of Lands, Ministry of Commerce, Trade & Industry | N500,000.00 | 2023-01-01 | 2023-10-31
|  |  | A.1. publication of the regulatory processes to include fees, services, delivery timelines in 5 Business Enabling Environment (BBE) MDAs on the State official website | Publish the business regulatory processes put in place on the official website of the State so that old and new business owners can access them easily | Ministry of Finance, Budget, and Economic Planning | Taraba State Investment Promotion Agency, Taraba State Signage and Advertising Agency, and Bureua of Lands, Ministry of Commerce, Trade & Industry | N450,000.00 | 2023-01-01 | 2023-10-31
|  |  | A.2. develop State Grievance Redress Mechanism with legal backing | TIPA will develop guidelines for Grievance Redress Mechanism (GRM) and ensure it has the required legal support | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry, and Ministry of Justice | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | A.3 development of Service level agreements (SLA) in the 5 BEE MDAs | The Office of the Head of Service shall coordinate the BEE MDAs to reach a level of agreement on service areas for each MDA to remove overlapping roles | Office of the Head of Service | Taraba State Investment Promotion Agency, Ministry of Housing, Taraba State Signage and Advertising Agency, and Bureua of Lands, Ministry of Commerce, Trade & Industry | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | A.4. issuance of State Executive Order to direct 5 BEE MDAs to publish on State offcial website(s) their fees, procedures, SLAs, GRM, and manadatory advance communication rule | An Executive order directing the BEE MDAs to publish their fees, procedures, SLAs, GRM and mandatory advance communication rule on the State official website | Taraba State Investment Promotion Agency | Office of the Head of Service, Secretary to the State Government | Not Applicable | 2023-01-01 | 2023-10-31
|  |  | A.5 online publication of the report on monthly basis the operation and implementation of the GRM and SLAs in the 5 BEE MDAs | Publish monthly reports on GRM and SLA compliance on the State website. | Taraba State Investment Promotion Agency | office of the Head of Service | Not Applicable | 2023-01-31 | 2023-10-31
5 | Domestic and external trade competitiveness | To reduce and regulate multiple formal and informal checkpoints on inter-state movement of goods | A. establishment and online publication of schedule of trade related fees and levies on inter-state movement of goods | Provide comprehensive information on schedule trade related fees and levies on inter- State movement of goods | Ministry of Industry, Trade and Investment | Bureau of Information and Communication Technology, and Taraba State Internal Revenue Service (TSIRS) |  | 2023-01-01 | 2023-10-31
|  |  | A.1. sensitization on the schedule of trade related fees and levies on inter- state movement of goods | Conduct advocacy meetings with groups and unions, emabrk on distribution of leaflets and lfiers to sensitize the operators | Ministry of Industry, Trade and Investment | Ministry of Information and Re-Orientation, Taraba State Internal Revenue Service |  | 2023-01-01 | 2023-03-31
|  |  | B. establishment of GRM for traders with SMS/hotline for reporting and redress | Establish an office and appoint a desk officer whose phone number shall be made available to the public to receive complaints | Taraba State Investment Promotion Agency | Ministry of Trade and Industry, Head of Service and Secretary to the State Government |  | 2023-01-01 | 2023-06-30
|  |  | B.1 reporting on issues which are addressed by the GRM on monhly basis | Produce a monthly report of their activities to the Ministry for monitoring purpose | Taraba State Investment Promotion Agency (TIPA) | BEE MDAs |  | 2023-06-30 | 2023-12-31
|  |  | C. establishment of State Committee on Export promotion (SCEP) | The Committee had been already been put in place | Ministry of Commerce, Trade and Industry | Ministry of Agric and Food Security, Nigerian Export Promotion Council |  | 2023-01-01 | 2023-12-31
|  |  | C.1 allocation of an operational budget to the SCEP in the 2024 budget | Ministry of Trade shall include the SCEP in its 2024 budget estimate | Ministry of Commerce, Trade and Industry | Ministry of Finance, Budget and Economic Planning |  | 2023-01-01 | 2023-12-31
|  |  | D. develop Taraba State export strategy and guidelines | A strategy leveraging the One State One product for Export national strategy should be developed | Once the Ministry of Commerce, Trade and Industry adopts the export strategy guideline, it wi+E69:E71 | Nigerian Export Promotion Council, Ministry of Agriculture and Food Security |  | 2023-01-01 | 2023-03-31
|  |  | D.1 online publication of Taraba State Export Strategy and Guildelines | Ministry of Commerce, Trade with BICT shall publish the State Export Strategy and Guildelines for easyaccessibility | Ministry of Commerce, Trade and Industry | Ministry of Information and Re-Orientation |  | 2023-04-01 | 2023-06-30
|  |  | E. eliminate haulage fees and charges in year 2024 | Ministry of Trade and other BEE MDAs shall gradually work out the removal of haulage fees and charges by end of 2025 by obtaining the approval of the Governor | Ministry of Commerce, Trade and Industry | Taraba State Internal Revenue Services,Ministry of Finance, Budget, and Economic Planning |  | 2023-12-01 | 2023-12-31
|  |  | F. increase the number of firms with export certificates from Nigerian Export Promotion Council (NEPC) attracted to Taraba State | SCEP and Ministry of Trade shall make sensitization campaign to attract new Exporters with incentives put in place to help Export business in the State | Ministry of Commerce, Trade and Industry | Nigerian Export Promotion Council, Ministry of Information |  | 2023-01-01 | 2023-10-31
6 | Simplification of State and Local Business Tax Regimes | This reform is aimed at making it easy to understand and make payment for tax in Taraba State | A. review the existing State revenue law to adopt presumptive turnover tax regime for small businesses | To review the Taraba State Board of Internal Revenue Law | Taraba State Internal Revenue Services | Ministry of Finance, Budget, and Economic Planning, Ministry of Justice and Taraba State House of Assembly |  | 2023-01-01 | 2023-06-30
|  |  | A.1 establish a presumptive turnover tax regime for small busniesses in Taraba State | Achieve 100% growth in both number of taxpayers and value of taxes collected | Taraba State Internal Revenue Services | Ministry of Industry, Trade and Investment, and Ministry of Local Government |  | 2023-01-01 | 2023-06-30
|  |  | B. subsume all business- related local government charges/fees/taxes into a consolidated demand notice | Generate harmonized Demand Notice | Taraba State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties |  | 2023-01-01 | 2023-04-01
|  |  | B.1 raise consolidated demand notices for all business-related local government charges/fees/taxes | Print and serve consolidated Demand Notices | Taraba State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties |  | 2023-03-31 | 2023-04-30
|  |  | C. establish electronic platform for collection of taxes,levies and fees from businesses and generate automated e-receipt (QR code or unique payment ID) for all BEE MDAs | Develop Electronic Payment Solution | Taraba State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties |  | 2023-01-01 | 2023-06-30
|  |  | D. ensure electronic payment of all State-level and local government taxes, levies and fees from business (with adoption of at least 75% of State collection of taxes, levies and fees from businesses | Increase adoption of electronic Payment of taxes | Taraba State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties |  | 2023-01-01 | 2023-12-31
7 | Quick determination of commercial disputes | This reform area will improve the State Judiciary and strengthen access to an efficient commercial justice system | A. establishment of State Judicial Committee by the Chief Judge of Taraba State Judiciary | The chief Judge of Taraba State Judiciary shall obtain the approval of the Governor for the establishment of Judicial Committee | Taraba State Judiciary | Ministry of Justice, Office of the Secretary to the State Government, |  | 2023-01-01 | 2023-12-30
|  |  | B. establishment and operation of small claims courts (tried at least one case each) | The Judicial Committee shall appoint some judges to preside over the small claims courts in the State | Taraba State Judiciary | Ministry of Justice |  | 2023-01-01 | 2023-01-31
|  |  | B.1 Development of the State Judiciary website | to ensure transparency, the State Judiciary shall establish a functional website | Taraba State Judiciary | Ministry of Justice |  | 2023-01-01 | 2023-06-30
|  |  | B.2 publication on State Judiciary website the practice Directions of the small claims courts | to ensure transparency, the State Judiciary shall establish a functional website | Taraba State Judiciary | Ministry of Justice, BICT |  | 2023-01-01 | 2023-06-30
|  |  | B.3. write monthly report for small claims courts from inception of thecourts to December 2023 | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis | Taraba State Judiciary | Ministry of Justice |  | 2023-01-01 | 2023-12-31
|  |  | B.4. publication on the State Judiciary website reports for small claims courts on monthly basis | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis | Taraba State Judiciary | Ministry of Justice |  | 2023-01-01 | 2023-10-30
|  |  | C. submit dispostion time report to include the % of cases dispose within 60 days | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis and ensuee at least 80% performance achievement | Taraba State Judiciary | Ministry of Justice |  | 2023-01-01 | 2023-10-30
|  |  | D. submit execution time report to include the % of judgement executed within 30 days | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis and ensuee at least 80% performance achievement | Taraba State Judiciary | Ministry of Justice |  | 2023-01-01 | 2023-10-30