## COVERPAGE
TARABA STATE BUSINESS-ENABLING REFORM ACTION PLAN (BERAP) 2025
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP)
State: | TARABA STATE
Reporting period: |  | FY 2024
SABER Focal Person: |  |  | NATAALA KAIGAMA
SABER PROGRAM MANAGER |  |  | CORNELIUS ADEOYE
Was this plan prepared in consultation with the Private Sector |  |  |  |  | Yes
|  |  | Public Sector | Private Sector
List of contributing entities: |  |  | Ministry of Budget and Economic Planning, Ministry of Finance Ministry of Business, Trade & Cooperatives Ministry of Physical Planning, Urban & Regional Development Ministry of Agriculture and Food Security Ministry of Environment and Sustainability Ministry of Road and Bridges Ministry of Communication and Orientation Ministry of Local Government and Communality Affairs Ministry of Justice/Attorney General Ministry of Home Affairs and Security Ministry of Mining and Energy Ministry of Social Development and Gender Issues Ministry of Youth & Humanitarian Affairs Ministry of Digital Economy, Science & Technology Taraba State Investment Promotion Agency Taraba State Board of Internal Revenue Taraba State Procurement Agency, Taraba State Geographic Information Service Tarabajobs Taraba State Building and Maintenance Agency Taraba State Signage Agency Taraba State Transport Authority, Taraba State Public, Private, Partnership Office Taraba State Information Communication Technology Agency Taraba State Electricity Regulatory Agency, Taraba State Forestry Commission. Taraba State Multi-Door Courthouse Taraba State Broadcasting Service | b) President Civil Society Organisation, c) Talcam Farm d) Thames International Group e) Farmview f) Cadsoft g) Lesney Partners, SMARTAPP TRCHNOLOGY
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  |  |  |  | Yes
If this was approved by SEC, please state date:

## BERAP2024
STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) PROGRESS REPORT- 2024
PROGRESS REPORT
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | STATUS | STATUS DESCRIPTION | NEXT STEP
| Improved Land Administration and Land Investment Process | Leverage digital solutions to streamline processes, enhance transparency, and minimize inefficiencies and fraud, ensuring fair and efficient land transactions. | A. Digitization and indexation of existing CofOs in a digital archive | Ensure at least 75% of existing certificates are digitzed and archived. | Investors, Urban and Rural Communities | Taraba State Geo Information Service GIS | SABER SECRETARIAT | N125,000,000.00 | 2024-01-01 | 2024-09-30 | COMPLETED This streamlines land-related transactions and encourages investment. | OVER 95% of existing certificates are digitized and archived. | continuous procrsss improvement
|  | ensure fair, transparent, and sustainable land acquisition for agricultural investments. | B. Establishment the Framework for Responsible and Inclusive Land Intensive Agriculture (FRILIA) as contained in the Executive Order 7 | (i) Set-up FRILIA Technical to develop FRILIA document to address challenges in Land administration for Agricultural and Industrial purposes in the State; (ii) create a Multistakeholders platfrom (MSP) for consultation on key issues | INVESTORS, FARMERS AND LAN OWNERS | Ministry of Agriculture and Food security | SABER SECRETARIAT | N40,000,000.00 | 2024-01-01 | 2024-09-30 | COMPLETEDThis framework facilitates better planning, allocation, and management of land resources, promoting responsible and inclusive land use practices | A FRILIA Technical Committee has been set up to develop the FRILIA document to address challenges in land administration for agricultural and industrial purposes, and a Multi-stakeholder Platform (MSP) has been created for consultation on key issues. | implimentation and monitoring of Frillia projects
|  |  | C. Adoption and implementation of the FRILIA | FRILIA Steering Committee shall ensure the adoption and implementation of FRILIA in the State | INVESTORS, BUSINESSES AND GOVERNMMENT | Ministry of Agriculture and Food security | SABER SECRETARIAT | N5,000,000.00 | 2024-01-01 | 2024-09-30 | COMPLETED. This ensures that the principles and guidelines developed for responsible and inclusive land intensive agriculture are applied in practice, leading to improved land administration and investment processes in the state. | The FRILIA Steering Committee has ensured the adoption and implementation of FRILIA in the State. | oversight funtion on frilia projects
[9 empty] | 2024-01-01 | 2024-09-30
2 | Improved infrastructure for enhacement of business-enabling environment (regulatory framework for private investment in fibre optic infrastructure) | To build a strong foundation for digital economy through enhaced fast, relaible and accessible fixed broadband to incentivised opertaors for the deployment of fixed broadband in the State. | A. Amendment of the existing legislation/regulations or passing of new legislation/regulation to adopt aggregate fees charged for broadband deployment on a per liner meter basis at a maximum of NGN145 per meter | Upgrade the existing Executive Order on broadband fees to a Law duly passed by the State House of Assembly | INVESTORS, BUSINESSES AND GOVERNMMENT | Ministry of Rural & Urban Development | Taraba State Internal Revenue Service, Ministry of Finance, Taraba State Investment Promotion Agency, Ministry of Works & Infrastructure Development, and Ministry of Justice | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED This encourages investment in broadband infrastructure, which is essential for enhancing the business-enabling environment and promoting digital transformation | State maintained aggregate per linear meter fees for broadband deployment and Published on state official. The 2023 executive order and regulations of 145 per linear meter maintained. . | total removal/waiver of right of way fees in 2025 to encourage wider broadband coverage acroos the state
|  |  | A.1. maintenace of the aggregate per linear meter fees for broadband deployment | Ensure a law that caps the Right of Way tariff at not more than N145 per linear meter is enacted. | INVESTORS, BUSINESSES AND GOVERNMMENT | Ministry of Works & Infrastructure Development | Ministry of Works & Infrastructure Developments, Ministry of Rural & Urban Development | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This makes it more affordable for telecommunications companies to lay fibre optic cables, leading to increased broadband penetration and improved internet connectivity for businesses and citizens. | A regulation that caps the Right of Way tariff at not more than N145 per linear meter maintained and published on the state website | total removal/waiver of right of way fees in 2025 to encourage wider broadband coverage acroos the state
|  |  | B. publication of Right of Way (ROW) process | Publish the ROW process on the State website | INVESTORS, BUSINESSES AND GOVERNMMENT | Ministry of Rural & Urban Development | Bureau of Information and Communication Technology, Ministry of Rural & Urban Development, Ministry of Infrastructure and Public Utility | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This makes it easier for telecommunications companies to understand the process, requirements, and timelines for obtaining ROW permits, reducing delays and facilitating faster infrastructure deployment. | The ROW process has been published on the State website. | MAINTAIN PUBLICATION IN 2025
|  |  | B.1 Establishment of framework for the ROW process in the State | Establish a framework for ROW deployment across the State | INVESTORS, BUSINESSES AND GOVERNMMENT | Ministry of Rural & Urban Development | Ministry of Works & Infrastructure Developments | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This reduces complexity and uncertainty for telecommunications companies, making it easier to plan and execute broadband infrastructure projects. | A framework for ROW deployment across the State has been established. | NOT/APPLICABLE
|  |  | B.2. Publish on the state official website, the process for obtaining ROW including all relevant MDAs, timeframes, and costs | Publish all ROW related processes and fees on the State website. |  | Ministry of Rural & Urban Development | Bureau of Information and Communication Technology, Taraba State Investment Promotion Agency, Ministry of Works & Infrastructure Developments | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This ensures TELECOM COMPANIES thave access to all the necessary details, including the relevant MDAs, timeframes, and costs, enabling them to navigate the ROW process more efficiently. | All ROW related processes and fees have been published on the State website | MAINTAIN PUBLICATION IN 2025
|  |  | C. deployment of non- Gigabit Passive Optical Network (GPON) fibre optic cable kilometres | Ensure deployment of GPON fibre infrastructure across Taraba State in at least 2,000km across the State. |  | Ministry of Works & Infrastructure Developments | Ministry of Rural & Urban Development, Office of the surveyor General and Ministry of Finance, Bureau of Information, Communication and Technology | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This provides businesses and citizens with access to high-speed internet, which is crucial for economic development, education, and access to information. | GPON fibre infrastructure has been deployed across Taraba State in at least 2,000km across the State. | NOT/APPLICABLE
|  |  | C.1 increase in total deployed GPON fibre optic cable kilometres against 2022 baseline meets target. Basic target: 20-99% Stretch target: ˃100% | The State shall ensure that ther is an increase of more that 100% in the total deployed GPON fibre optic cable kilometers against 2022 as baseline |  | Ministry of Rural & Urban Development | Taraba State Development and Investment Promotion Agemcy, Ministry of Housing and Bureua of Lands | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. improved internet connectivity and creating a more favorable business environment. | The State has ensured an increase of more than 100% in the total deployed GPON fibre optic cable kilometers against 2022 as baseline. | NOT/APPLICABLE
3 | Sustainable Large- Scale Investments | (i) to have an effective State invetsment promotion agency for service delivery to investors and targeted efforts towards attracting and retaining investment (ii) to ensure transparency and easier access to information and participation for stimulation of investment in the economy of the State; (iii) to establish effective Public-Private Partnership (PPP) models in the State | A. mandate Taraba Development and Investment Promotion Agency (TIPA) (state-level technical unit/agency) as the lead organization to facilitate PPP and promote investment into the State | Enact a Law establishing a State Investment Promotion Agency and develop a strategic plan to operationalise the agency. |  | Taraba State Investment Promotion Agency (TIPA) | Ministry of Industry, Trade and Investment, and the Ministry of Justice | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. TIPA plays a crucial role in attracting domestic and foreign investment, promoting Public-Private Partnerships (PPPs), and supporting businesses operating in the state. | A Law establishing a State Investment Promotion Agency has been enacted, and a strategic plan to operationalize the agency has been developed
|  |  |  | Enact and implement a State Public Private Partnership Law designatingTIPA as lead agency for PPP facilitation |  | Taraba State Investment Promotion Agency | Ministry of Industry, Trade and Investment, Ministry of Justice and Taraba State House of Assembly | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. Taraba State Public Private Partnership Executive Order 7 signed by the Governor of the state | PPP unit is established and operational
|  |  | B. Establishment of effective PPP models | Develop and agree frameworks to determine the PPP models required for various investment opportunities in the State. |  | Taraba State Investment Promotion Agency | Ministry of Industry, Trade and Investment, and the Ministry of Justice | N50,000,000.00 | 2024-01-01 | 2024-09-30 | COMPLETED. This ensures that the most appropriate PPP models are used for different investment projects, maximizing their potential for success and contributing to economic development. | Frameworks have been developed and agreed upon to determine the PPP models required for various investment opportunities in the State.
|  |  | B.1 establishment of Taraba State Fiscal Commitment and Contigent Liability (FCCL) Management Framework | Develop an a Fiscal Commitment and Contigency Liability Management Framework |  | Ministry of Finance, Budget, and Economic Planning | Ministry of Budget and Economic Planning, TIPA | N2,500,000.00 | 2024-01-01 | 2024-09-30 | COMPLETED. This framework helps to assess and mitigate financial liabilities, ensuring the long-term sustainability of investment initiatives. | A Fiscal Commitment and Contingency Liability Management Framework has been developed.
|  |  | B.2 establishment of PPP legal and institutional framework, inluding guidelines and manual | TIPA to develop guidelines and manual of PPP framework. The beneficiaries are the investors and business owners. |  | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | N1,000,000,00 | 2024-01-01 | 2024-09-30 | COMPLETED. This framework outlines the legal and institutional aspects of PPPs, ensuring transparency, fairness, and adherence to best | TIPA has developed guidelines and a manual for the PPP framework.
|  |  | B.3 establishment of the PPP disclosure Framework | PPP franework established and published on TIPA /PPP website | Investors | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | N1,000,000,00 | 2024-01-01 | 2024-09-30 | COMPLETED. This framework provides stakeholders with access to information about PPP projects, including their objectives, scope, and progress, fostering trust and encouraging participation | The PPP framework has been established and published on the TIPA/PPP website.
|  |  | B.4 online publication of the (i) PPP Fiscal Commitment and Contigent Liability (FCCL) Management Framework; and (ii) PPP legal and institutional framework, including guidelines and manual; and (iii) PPP disclosure framework | (i) Develop FCCL Management framework (ii) Develop PPP Guidelines and manual and (III) PPP disclosure framework | Investors | Taraba State Investment Promotion Agency | Ministry of Justice | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This enhances transparency, facilitates informed decision-making, and promotes a more favorable investment environment. | The FCCL Management framework, PPP Guidelines and manual, and PPP disclosure framework have been developed.
|  |  | B.5. adoption and disclosure of PPP pipeline by TIPA (of which at least 50% is linked to climate adaptation and mitigation | Publish a list of PPP projects and their respective status to promote transparency. |  | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This pipeline provides potential investors with visibility into available investment opportunities and demonstrates the state's commitment to sustainable development | A list of PPP projects and their respective status has been published to promote transparency.
|  |  | B.6. online publication (or web-based disclosure portal) of the pipeline projects | TIPA to publish pipeline projects on her website. The beneficiaries are the potential investors, investors and business |  | Taraba State Investment Promotion Agency | Ministry of Information and Re-Orientation | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This online platform serves as a central hub for information about PPP projects, facilitating investor engagement and promoting investment in the state. | TIPA has published pipeline projects on PPP website.
|  |  | C. establishment of State Project Facilitation Fund with a minimum funding of 3% of the total pipeline estimated capital investment | Establisha State Wealth Fund which will include Project Facilitation Fund to catalyze private investments |  | Ministry of Finance, Budget, and Economic Planning | Taraba State Investment Promotion Agency, Ministry of Budget ,and Economic Planning, Ministry of Justice, and Ministry of Commerce, Trade & Industry | N500,000,000 | 2024-01-01 | 2024-09-30 | COMPLETED. This fund helps to de-risk investment projects, attract co-financing, and facilitate the implementation of priority PPPs, contributing to economic growth and job creation. | A State Wealth Fund has been established, which includes a Project Facilitation Fund to catalyze private investments.
|  |  | D. develop/update an inventory/database of all investment incentives (Federal and State) available in Taraba State | Inventory of all investment incentives in the State alreadydeveloped and published on TIPA website. The beneficiaries are the investors and bussiness owners. |  | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This inventory helps investors identify relevant incentives, reduce investment costs, and make informed decisions about investing in the state. | An inventory of all investment incentives in the State has been developed and published on the TIPA website.
|  |  | D.1. online publication of the inventory all investment incentives available in the State | Inventory of all investment incentives in the State already published on TIPA website. The beneficiaries are the investors and bussiness owners. |  | Taraba State Investment Promotion Agency | Bureau of Information and Communication Technology | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This online resource helps to attract investment by highlighting the favorable investment environment and available support mechanisms. | An inventory of all investment incentives in the State has been published on the TIPA website.
|  |  | E. Update of TIPA website with required information (including information on access to credit) | TIPA website to be updated with required information. The beneficiaries are the investors, business owners and potential investors |  | Taraba State Investment Promotion Agency | Bureau of Information and Communication Technology | N10,000,000.00 | 2024-01-01 | 2024-09-30 | COMPLETED.This includes information about investment opportunities, incentives, and access to credit, facilitating investor engagement and promoting investment in the state. | The TIPA website has been updated with required information. Including accces to credit and link to NEPC website
|  |  | F. organization of quaterly information sessions annually for investors by TIPA | Ensure at least 2 sessions are held in 2023 to engage with investors operating in Taraba State, to discuss among others Business Environment Reforms and tax compliance. |  | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry And Taraba State Internal Revenue Service | N5,000,000.00 | 2024-01-01 | 2024-09-30 | COMPLETED. These sessions provide a platform for discussing business environment reforms, addressing investor concerns, and promoting tax compliance, contributing to a more favorable investment climate. | At least 2 sessions were held in 2024 to engage with investors operating in Taraba State, discussing Business Environment Reforms, ACCESS TO CREDIT and tax compliance.
|  |  | G. development and adoption of aftercare and retention program | Develop and implement an aftercare programe that caters to existing investors. |  | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry | N1,500,000.00 | 2023-01-01 | 2023-01-31 | COMPLETED. This program provides support and assistance to businesses operating in the state, addressing their needs and challenges, and encouraging them to expand their investments. | An aftercare program that caters to existing investors has been developed and implemented.
4 | Increased Transparency of official fees and procedures | (i) This reform area will increase transparency of official fees and procedures focusing on key business environment enabling MDAs in Taraba State; (ii) the reform will give easier access to regular information for greater regulatory efficiency, lower compliance costs and better regulatory quality; (iii) Reduce overlapping of licensing requirements; (iv) reduce potential discretionary behaviors | A. mapping and developing business regulatory processes in 5 BEE MDAs | Taraba State Ministry of Finance shall work with the selected BEE MDAs to develop a business regulatory processes inclusive of fee structures in the State. | INVESTORS AND TRADERS | Ministry of Finance, Budget, and Economic Planning | Taraba State Investment Promotion Agency, Ministry of Housing, Taraba State Signage and Advertising Agency, and Bureua of Lands, Ministry of Commerce, Trade & Industry | N500,000.00 | 2024-01-01 | 2024-09-30 | COMPLETED. Easy step by step guide for businesses and investor
|  |  | A.1. publication of the regulatory processes to include fees, services, delivery timelines in 5 Business Enabling Environment (BBE) MDAs on the State official website | Publish the business regulatory processes put in place on the official website of the State so that old and new business owners can access them easily | INVESTORS AND TRADERS | Ministry of Finance, Budget, and Economic Planning | Taraba State Investment Promotion Agency, Taraba State Signage and Advertising Agency, and Bureua of Lands, Ministry of Commerce, Trade & Industry | N450,000.00 | 2024-01-01 | 2024-09-30 | COMPLETED.This online resource helps to attract investment by making available online transparent processes fees and service delivery timeline.
|  |  | A.2. develop State Grievance Redress Mechanism with legal backing | TIPA will develop guidelines for Grievance Redress Mechanism (GRM) and ensure it has the required legal support | INVESTORS AND TRADERS | Taraba State Investment Promotion Agency | Ministry of Commerce, Trade & Industry, and Ministry of Justice | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED.This has help establish a formal system for addressing grievances, providing a structured approach for individuals and businesses to report issues and seek resolution | Digital GRM has been developed for easy accessibilityrecording and tracking resolution
|  |  | A.3 development of Service level agreements (SLA) in the 5 BEE MDAs | The Office of the Head of Service shall coordinate the BEE MDAs to reach a level of agreement on service areas for each MDA to remove overlapping roles | INVESTORS, TRADERS AND GENERAL PUBLIC | Office of the Head of Service | Taraba State Investment Promotion Agency, Ministry of Housing, Taraba State Signage and Advertising Agency, and Bureua of Lands, Ministry of Commerce, Trade & Industry | Not Applicable | 2024-01-01 | 2024-09-30 | COMPLETED. This will help to clearly define the expected level of service, timelines, and responsibilities, leading to improved efficiency and transparency in the interactions between businesses and government agencies. | SLA developed for the 5 BEEs MDA
|  |  | A.4. issuance of State Executive Order to direct 5 BEE MDAs to publish on State offcial website(s) their fees, procedures, SLAs, GRM, and manadatory advance communication rule | An Executive order directing the BEE MDAs to publish their fees, procedures, SLAs, GRM and mandatory advance communication rule on the State official website | NVESTORS, TRADERS AND GENERAL PUBLIC | Taraba State Investment Promotion Agency | Office of the Head of Service, Secretary to the State Government | Not Applicable | 2023-01-01 | 2024-09-30 | COMPLETED. This will increase transparency and provide businesses with easy access to important information regarding regulations and processes. | EXECUTIVE ORDER 8 SIGNED by Governor of Taraba directing Transparency in Government Fees Procedure and commitment to SLA
|  |  | A.5 online publication of the report on monthly basis the operation and implementation of the GRM and SLAs in the 5 BEE MDAs | Publish monthly reports on GRM and SLA compliance on the State website. | NVESTORS, TRADERS AND GENERAL PUBLIC | Taraba State Investment Promotion Agency | office of the Head of Service | Not Applicable | 2023-01-31 | 2024-09-30 | COMPLETED.This regular reporting and publication will help identify areas for improvement, build trust between the government and the business community, and contribute to a more efficient and responsive business environment. | online publication of the report on monthly basis the operation and implementation of the GRM and SLAs in the 5 BEE MDAs | c
5 | Domestic and external trade competitiveness | To reduce and regulate multiple formal and informal checkpoints on inter-state movement of goods | A. establishment and online publication of schedule of trade related fees and levies on inter-state movement of goods | Provide comprehensive information on schedule trade related fees and levies on inter- State movement of goods |  | SABER SECRETARIAT | Bureau of Information and Communication Technology, and Taraba State Internal Revenue Service (TSIRS) |  | 2024-01-01 | 2024-09-30 | COMPLETED. make this information readily available to operators. This transparency allows businesses involved in inter-state trade to be aware of the costs associated with moving goods, which can help them with planning, budgeting, and compliance. Making the schedule publicly available online ensures easy access and reduces the potential for arbitrary or unclear charges. | establishment and online publication of schedule of trade related fees and levies on inter-state movement of goods
|  |  | A.1. sensitization on the schedule of trade related fees and levies on inter- state movement of goods | Conduct advocacy meetings with groups and unions, emabrk on distribution of leaflets and lfiers to sensitize the operators |  | Ministry of Industry, Trade and Investment | Ministry of Information and Re-Orientation, Taraba State Internal Revenue Service |  | 2024-01-01 | 2024-09-30 | COMPLETED. This understanding helps operators comply with regulations, plan their logistics and costs effectively, and reduces instances of misunderstandings or disputes regarding fees and levies. | conducted advocacy meetings with groups and unions, and embark on the distribution of leaflets and fliers to sensitize the operators.
|  |  | B. establishment of GRM for traders with SMS/hotline for reporting and redress | Establish an office and appoint a desk officer whose phone number shall be made available to the public to receive complaints | ALL STAKEHOLDERS | Taraba State Investment Promotion Agency | Ministry of Trade and Industry, Head of Service and Secretary to the State Government |  | 2024-01-01 | 2024-09-30 | COMPLETED. The SMS/hotline feature makes it easier for traders to communicate their grievances, leading to quicker reporting and potentially faster redress. This mechanism aims to create a more responsive system for addressing the concerns of traders, which can contribute to a more favorable trading environment. | stablished GRM for traders with SMS/hotline for reporting and redress
|  |  | B.1 reporting on issues which are addressed by the GRM on monhly basis | Produce a monthly report of their activities to the Ministry for monitoring purpose | ALL STAKEHOLDERS | Taraba State Investment Promotion Agency (TIPA) | BEE MDAs |  | 2024-01-01 | 2024-09-30 | COMPLETED. It contributes to transparency and helps in making data-driven decisions to improve the trading environment and the GRM | grm statistics is publishedmonthly on the state offivcial website
|  |  | C. establishment of State Committee on Export promotion (SCEP) |  | EXPORTERS AND INVESTORS | Ministry of Commerce, Trade and Industry | Ministry of Agric and Food Security, Nigerian Export Promotion Council |  | 2024-01-01 | 2024-09-30 | COMPLETED. A commitment by the state government to boost export activities, which can lead to economic growth, increased foreign exchange earnings, and the creation of jobs. | SCEP AESTABLISHED under ministry of Commerce trade and investment
|  |  | C.1 allocation of an operational budget to the SCEP in the 2024 budget | Ministry of Trade shall include the SCEP in its 2024 budget estimate | EXPORTERS AND INVESTORS | Ministry of Commerce, Trade and Industry | Ministry of Finance, Budget and Economic Planning |  | 2024-01-01 | 2024-09-30 | COMPLETED. SCEP organised sensitization and training for stakeholders to promote exports | Ministry of commerce allocated an operational budget of 90million to the SCEP in the 2024 budget for export activities
|  |  | D. develop Taraba State export strategy and guidelines | A strategy leveraging the One State One product for Export national strategy should be developed | EXPORTERS AND INVESTORS | Once the Ministry of Commerce, Trade and Industry adopts the export strategy guideline, it wi+E69:E71 | Nigerian Export Promotion Council, Ministry of Agriculture and Food Security |  | 2024-01-01 | 2024-09-30 | COMPLETED. provide a clear roadmap and framework for promoting exports from the state. | developed Taraba State export strategy and guidelines
|  |  | D.1 online publication of Taraba State Export Strategy and Guildelines | Ministry of Commerce, Trade with BICT shall publish the State Export Strategy and Guildelines for easyaccessibility | EXPORTERS AND INVESTORS | Ministry of Commerce, Trade and Industry | Ministry of Information and Re-Orientation |  | 2024-01-01 | 2024-09-30 | COMPLETED. online publication serves as a crucial step in disseminating the export strategy and guidelines, maximizing their potential impact on the state's export performance and economic development. | Publication of state export strategy anf guidelline on the state official website
|  |  | E. Consultation eliminate haulage fees and charges | Ministry of Trade and other BEE MDAs shall gradually work out the removal of haulage fees and charges by end of 2025 by obtaining the approval of the Governor | TRANSPORTERS | Ministry of Commerce, Trade and Industry | Taraba State Internal Revenue Services,Ministry of Finance, Budget, and Economic Planning |  | 2024-01-01 | 2024-09-30 | ONGOING . This action aims to reduce the cost of moving goods, which can benefit traders and businesses involved in inter-state movement.
|  |  | F. increase the number of firms with export certificates from Nigerian Export Promotion Council (NEPC) attracted to Taraba State | SCEP and Ministry of Trade shall make sensitization campaign to attract new Exporters with incentives put in place to help Export business in the State | BUSINESSES, INVESTORS AND EXPORTERS | Ministry of Commerce, Trade and Industry | Nigerian Export Promotion Council, Ministry of Information |  | 2024-01-01 | 2024-09-30 | COMPLETED. 3 taraba firms obtained NEPC export cerificate , Builds a more competitive and export-ready ecosystem and economic growth | increase in the number of firms with export certificates from Nigerian Export Promotion Council (NEPC) attracted to Taraba State
6 | Simplification of State and Local Business Tax Regimes | This reform is aimed at making it easy to understand and make payment for tax in Taraba State | A. review the existing State revenue law to adopt presumptive turnover tax regime for small businesses | To review the Taraba State Board of Internal Revenue Law | BUSINESSES AND INVESTORS | Taraba State Internal Revenue Services | Ministry of Finance, Budget, and Economic Planning, Ministry of Justice and Taraba State House of Assembly |  | 2024-01-01 | 2024-09-30 | COMPLETED. Simplified Tax Compliance: Small businesses no longer need to maintain complex financial records. Tax is calculated based on estimated turnover, reducing administrative burden. | Establishment of the presumptive turnover tax regime in Taraba State.
|  |  | A.1 establish a presumptive turnover tax regime for small busniesses in Taraba State | Achieve 100% growth in both number of taxpayers and value of taxes collected | BUSINESSES AN\MD INVESTORS | Taraba State Internal Revenue Services | Ministry of Industry, Trade and Investment, and Ministry of Local Government |  | 2024-01-01 | 2024-09-30
[9 empty] | 2024-01-01 | 2024-09-30 | COMPLETED. | Target: Achieve 100% growth in: The number of registered small business taxpayers, and The value of taxes collected from this group.
|  |  | B. subsume all business- related local government charges/fees/taxes into a consolidated demand notice | Generate harmonized Demand Notice | GOVERNMENT, BUSINESESS, AND INVESTORS | Taraba State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties |  | 2024-01-01 | 2024-09-30 | COMPLETED. simplifies compliance for businesses by presenting a unified, itemized bill that enhances transparency and predictability, while also improving government efficiency by reducing administrative overlap, | Central State Billing platform deployed and can generate harmonised demand notice for for Businesses across the state
|  |  | B.1 raise consolidated demand notices for all business-related local government charges/fees/taxes | Print and serve consolidated Demand Notices | GOVERNMENT, BUSINESESS, AND INVESTORS | Taraba State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties |  | 2024-01-01 | 2024-09-30 | COMPLETED. simplifies compliance for businesses by presenting a unified, itemized bill that enhances transparency and predictability, while also improving government efficiency by reducing administrative overlap, | Billing platform can Print and serve consolidated Demand Notices
|  |  | C. establish electronic platform for collection of taxes,levies and fees from businesses and generate automated e-receipt (QR code or unique payment ID) for all BEE MDAs | Develop Electronic Payment Solution | GOVERNMENT, BUSINESESS, AND INVESTORS | Taraba State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties |  | 2024-01-01 | 2024-09-30 | COMPLETED boosts revenue, reduces fraud, improves taxpayer convenience, enhances transparency, and strengthens government efficiency | established electronic platform for collection of taxes,levies and fees from businesses and generate automated e-receipt (QR code or unique payment ID) for all BEE MDAs
|  |  | D. ensure electronic payment of all State-level and local government taxes, levies and fees from business (with adoption of at least 75% of State collection of taxes, levies and fees from businesses | Increase adoption of electronic Payment of taxes | GOVERNMENT, BUSINESESS, AND INVESTORS | Taraba State Internal Revenue Services | Ministry of Local Government, Ministry of Trade and Ministry of Infrastructure and Public Utilties |  | 2024-01-01 | 2024-09-30 | COMPLETED. adoption enhances transparency, reduce leakages, boost internally generated revenue, and improve ease of doing business. It streamlines processes, increases taxpayer trust, and supports data-driven governance across Taraba State. | over 75% of State collection of taxes, levies and fees from businesses are collected via electronic platform | contnuos onboarding of all MDAS fees levies and charges until 100% adoption is achieved
7 | Quick determination of commercial disputes | This reform area will improve the State Judiciary and strengthen access to an efficient commercial justice system | A. establishment of State Judicial Committee by the Chief Judge of Taraba State Judiciary | The chief Judge of Taraba State Judiciary shall obtain the approval of the Governor for the establishment of Judicial Committee | BUSINESSES AND INVESTORD | Taraba State Judiciary | Ministry of Justice, Office of the Secretary to the State Government, |  | 2024-01-01 | 2024-09-30 | COMPLETEDsignificantly strengthen judicial governance and accountability.enhance transparency | Chief Judge established the Judiciary Commmitte | N/A
|  |  | B. establishment and operation of small claims courts (tried at least one case each) | The Judicial Committee shall appoint some judges to preside over the small claims courts in the State | BUSINESSES AND INVESTORD | Taraba State Judiciary | Ministry of Justice |  | 2024-01-01 | 2024-09-30 | COMPLETED. Streamlined and faster processing of traded dispute resolution under N3million and reduction in case backlog | small claims court created in wukari, jalingo, bali and Gembu | N/A
|  |  | C. submit execution time report to include the % of judgement executed within 30 days | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis and ensuee at least 80% performance achievement | BUSINESSES AND INVESTORD | Taraba State Judiciary | Ministry of Justice |  | 2024-01-01 | 2024-09-30 | COMPLETED. boosts court efficiency, promotes accountability, builds public trust, and improves contract enforcement—strengthening Taraba’s justice system and business confidence. | Report template is developed. all execution report submitted and published on small claims court website | N/A